## Slide 1: Gantt Chart Schedule

## Slide 2: Module Learning Objectives
History of Gantt Chart Schedule
How to create a Gantt Chart
Types of Gantt Charts
How to Create a Gantt Chart using Microsoft Excel

## Slide 3: Gantt (Bar) Chart Schedule
History
  The development of the bar chart dates back to World War I, when Henry L. Gantt used the bar chart method of scheduling to plan and control military operations. In honor of Gantt’s early development of bar chart scheduling, you will often hear the term Gantt chart when referring to a bar chart. For practical purposes, the terms Gantt chart, Gantt schedule, or bar chart schedule are one and the same.

## Slide 4: Gantt (Bar) Chart Schedule
Definition
  A bar chart is ‘‘a graphic representation of project activities, shown in a time-scaled bar line’’

## Slide 5: Gantt (Bar) Chart Schedule

## Slide 6: Gantt (Bar) Chart Schedule
Creating Bar Charts
  The creation of a hand-drawn bar chart schedule is a relatively simple process
  Step 1: Using a piece of graph paper, write the calendar date across the top of the page. Some managers like to list the work day as well.
    The time scale is typically based on units of days, but for a summary bar chart or long-range planning (when less detail is necessary) it is common to use units of weeks, months, quarters, or even years

## Slide 7: Gantt (Bar) Chart Schedule
Creating Bar Charts
  Step 2: list the activities required to complete the project on the left side of the paper. As the activities are listed, put them in chronological order.
  Step 3: Determine the durations of activities. The duration should be based on productivity records, available resources, and experience. We will learn how to determine duration of activities in more detail later in this course

## Slide 8: Gantt (Bar) Chart Schedule
Creating Bar Charts
    Step 4: show or plot a bar on the dates when that activity is expected to take place. Commonly bars are shaded. For example, This beginning bar chart shows Survey as the first activity, which is scheduled to take place on the first work day, July 1. Continue listing the activities in chronological order with their corresponding bars as shown in the Figure.
    Read page 28-29 from handout “Bar Chart Schedules”

## Slide 9: Gantt (Bar) Chart Schedule
Creating Bar Charts
    Example
    Your project manager asks you to buy a piece of equipment for a project. Develop a Gantt chart for this activity. Start day Sep 12th
Calendar Day |  | 09/12 | 09/13 | 09/14 | 09/15 | 09/16 | 09/17 | 09/18 | 09/19 | 09/20 | 09/21
Activity Description Dur |  | 1 | 2 | 3 | 4 | 5 | W | W | 6 | 7 | 8
Determine equipment requirements | 1 |  |  |  |  |  |  |  |  |  | 
Determine budget | 1 |  |  |  |  |  |  |  |  |  | 
Research Brands and Models and Select | 3 |  |  |  |  |  |  |  |  |  | 
Check On-line and local outlets | 2 |  |  |  |  |  |  |  |  |  | 
Select Retailer and Purchase | 1 |  |  |  |  |  |  |  |  |  | 

## Slide 10: Gantt (Bar) Chart Schedule
Creating Bar Charts
    Class Exercise
    You are the head of engineering of a company. Recently a quality control engineer is retired and you need to hire a new quality control engineer to replace the position. Develop a Gantt chart for this hiring project with at least 8 tasks/activities. Project start second Monday of June.

## Slide 11: Gantt (Bar) Chart Schedule
Creating Bar Charts
0

## Slide 12: Gantt (Bar) Chart Schedule
Advantages of Bar Charts
  Simple and ease of prepare and understand
  Bar charts are time-scaled. Just by looking at the chart one can get an idea on the duration of each activity.
  Bar charts particularly appeal to persons who do not have a technical background.

## Slide 13: Gantt (Bar) Chart Schedule
What are the disadvantages of Bar Charts
  The main disadvantage of bar charts is lack of logical representation (relationships): Why did this activity start on that date? Bar charts do not reveal the answer. It could be a logical relationship, a resource constraint, or a subjective decision by the project manager/scheduler/owner
  Not easily modified
  Bar charts may not be practical for complex projects with large numbers of activities
0

## Slide 14: Gantt (Bar) Chart Schedule
Various Types of Bar Charts
  Bar charts have become a vehicle for representing many pieces of a project’s information. Many variations of bar charts have evolved
    Bar chart loaded with construction labor hours

## Slide 15: Gantt (Bar) Chart Schedule
Various Types of Bar Charts
  Bar charts have become a vehicle for representing many pieces of a project’s information. Many variations of bar charts have evolved
    Bar chart loaded with construction budget

## Slide 16: Gantt (Bar) Chart Schedule
Various Types of Bar Charts
  Bar charts have become a vehicle for representing many pieces of a project’s information. Many variations of bar charts have evolved
    Bar chart shows comparison between as planned vs as built

## Slide 17: How to Create a Gantt Chart using Microsoft Excel
  Click on the link below to learn how to create an automated Gantt (bar) chart in Microsoft Excel
  https://www.youtube.com/watch?v=6MOw3qDG4iI